## Slide 1
Software Project Management
Lab 7
Mansoura University Faculty of Computers and Information Department of Computer Science Second Semester- 2025-2026
Basma Yasser

## Slide 2: Outlines
Work Breakdown Structure.
WBS Dictionary.

## Slide 3: Work Breakdown Structures
Work breakdown structure (WBS) is a hierarchical tree structure that outlines your project and breaks it down into smaller, more manageable portions.
It's a way to divide large projects so you can get things done faster and more efficiently.
Each level of the work breakdown structure provides further definition and detail.​

## Slide 4: WBS Dictionary
The WBS Dictionary describes each component of the WBS with activities, scope, and sometimes dates, resources, and costs.​
Task Name​ |  |  | 
Start Date​ | End Date​ | Responsible​ | Participating Partners​
Work Statement​ |  |  | 
Activities |  |  | 
Cost items​ |  |  | 

## Slide 5
Construction of a house
Foundation
Excavation
Concrete
Finish works
Electrical works
Interior design
Decide furnitures
Procure furniture
Masonary works
Sanitary works
Painting works
Flooring works
A Work Breakdown Structure For Building a House.​

## Slide 6
1.1 Foundation​ |  |  | 
Start Date​ 3/4/2020​ | End Date​ 3/5/2020​ | Responsible​ X | Participating Partners​ x1,x2,x3….​
Work Statement​ | All of the work necessary to build a house.​ |  | 
Activities | Excavation and concrete​ |  | 
Cost items​ | 1000$​ |  | 

## Slide 7
1.1.1 Excavation |  |  | 
Start Date​ 4/4/2020​ | End Date​ 10/4/2020​ | Responsible​ X | Participating Partners​ x1,x2….​
Work Statement​ | Creating a hole to be framed and poured.​ |  | 
Cost items​ | 500$​ |  | 

## Slide 8
1.2 Masonary work |  |  | 
Start Date​ 28/4/2020​ | End Date​ 28/5/2020​ | Responsible​ Y | Participating Partners​ y1,y2….​
Work Statement​ | Building of structures from individual units.​ |  | 
Cost items​ | 1000$​ |  | 

## Slide 9
1.3 Finishing work |  |  | 
Start Date​ 10/5/2020​ | End Date​ 10/7/2020​ | Responsible​ Y | Participating Partners​ y1,y2….​
Work Statement​ | All of the work necessary to complete the interior of the house.​ |  | 
Activities | It contains some works such as Electricity and Plumbing, painting and flooring.​​ |  | 
Cost items​ | 1000$​ |  | 

## Slide 10
1.3.1 Electrical works |  |  | 
Start Date​ 11/5/2020​ | End Date​ 25/5/2020​ | Responsible​ X | Participating Partners​ x1,x2….​
Work Statement​ | All of the work necessary to complete the electrical works of the house.​ |  | 
Cost items​ | 700$​ |  | 

## Slide 11
New product launch
Planning
Setup team & budget
Sales
Organize sales channels
Product
Marketing
Define components of the product
Prepare product demo
Setup timeline & roadmap
Defining prices policies
Organize online sales
Organize advertising
Plan events & trade shows
Update corporate website
A Work Breakdown Structure For launching a new product​

## Slide 12
1.1 Planning |  |  | 
Start Date​ 1/5/2020​ | End Date​ 8/5/2020​ | Responsible​ x | Participating Partners​ x1,x2….​
Work Statement​ | Defining the requirements.​ |  | 
Activities | Setup Team & Budget,​ Define the components of product and​ Setup timeline and roadmap​​ |  | 
Cost items​ | Only time spent |  | 

## Slide 13
1.2 Product |  |  | 
Start Date​ 10/5/2020​ | End Date​ 20/5/2020​ | Responsible​ Y | Participating Partners​ y1,y2….​
Work Statement​ | Identifying everything about our new product.​ |  | 
Activities | Prepare product demo,​ Defining prices policies |  | 
Cost items​ | Only time spent |  | 

## Slide 14
1.3 Marketing |  |  | 
Start Date​ 10/5/2020​ | End Date​ 20/5/2020​ | Responsible​ Y | Participating Partners​ y1,y2….​
Work Statement​ | bringing a new product to market and overseeing its overall success.​ |  | 
Activities | Organize advertising,​ Plan events and trade shows and​ Update corporate website |  | 
Cost items​ | 1000$ |  | 

## Slide 15
Software development
SW Requirements
Draft preliminary software requirements
Develop delivery timeline
Design
UX/UI
Development
Testing
Database
Coding
Unit testing
System testing
A Work Breakdown Structure For building a Software system​

## Slide 16
1.1 SW Requirements |  |  | 
Start Date​ 10/5/2020​ | End Date​ 20/5/2020​ | Responsible​ Y | Participating Partners​ y1,y2….​
Work Statement​ | Defining the requirements​.​ |  | 
Activities | Draft preliminary software requirements​ Develop delivery timeline​ |  | 

## Slide 17
1.3 Development |  |  | 
Start Date​ 10/6/2020​ | End Date​ 20/10/2020​ | Responsible​ Y | Participating Partners​ y1,y2….​
Work Statement​ | Developing the core of the system​.​ |  | 
Activities | Database​ Coding​ |  | 

## Slide 18
1.4 Testing |  |  | 
Start Date​ 25/10/2020​ | End Date​ 25/12/2020​ | Responsible​ Y | Participating Partners​ y1,y2….​
Work Statement​ | Evaluating the system to find whether it satisfies the specified requirements or not​.​ |  | 
Activities | Unit Testing​ System Testing​ |  | 

## Slide 19
Thank You